## Migration Tracker
EXCHANGE MIGRATION TRACKER ¦ Vendor Decommission → In-House System ¦ CONFIDENTIAL
Prepared by: Strategy & Technology ¦ Date: 30 Jun 2026 ¦ Version: 2.0 — 30 Exchanges ¦ Classification: Internal – Restricted
# | Exchange Name | Priority (1=High) | Description / Business Role | Why We Use This Exchange | Platform ADV (Daily Vol, $M) | Our Volume on Exchange ($M/day) | Deals Traded Through Platform (Monthly) | Asset Classes / Products | What's on the Table | Risks & Dependencies | Critical? (Y/N) | Reason for Criticality | Est. Annual Cost (Vendor) ($K) | Est. Annual Cost (In-House) ($K) | Est. Cost Saving ($K/yr) | ETA Exchange Setup | Migration Status | Notes / Actions
1 | CME Group | 1 | Premier global derivatives exchange for interest rate, equity index, FX, and commodity futures. | Sole venue for many regulated futures contracts core to macro hedging strategy; deepest liquidity in rates complex. | 420000 | 890 | 3100 | Interest Rate Futures, Equity Index Futures, FX Futures | Migrate FCM relationship and clearing connectivity to in-house order routing. | FCM clearing transition risk; margin methodology differences (SPAN vs in-house); regulatory reporting continuity. | Y | Core macro hedging venue; rates futures positions cannot be easily rerouted; clearing relationship is foundational. | 710 | 140 | 570 | Oct 2025 | Scoping | Coordinate with clearing broker on account transfer timeline.
2 | NYSE | 2 | Primary US listed equities exchange; largest source of large-cap equity execution. | Best execution venue for large-cap US equities; required for certain index arb and basket trading strategies. | 312000 | 640 | 1900 | Listed Equities, ETFs | Migrate DMA (direct market access) connectivity and smart order routing logic in-house. | SEC Reg NMS compliance continuity; smart order router recalibration; best-execution reporting obligations. | Y | Core US equity execution venue; best-execution obligations under Reg NMS make this compliance-critical. | 540 | 105 | 435 | Oct 2025 | Scoping | Confirm DMA sponsor relationship survives vendor transition.
3 | Binance | 3 | World's largest centralised crypto exchange; core venue for spot, futures, and options. | Dominant global liquidity pool; tightest spreads on BTC/ETH; primary venue for block execution and delta hedging. | 85000 | 520 | 2400 | Spot, Futures, Options, Margin | Migrate API key mgmt, execution algos, and post-trade reporting to proprietary OMS. | API rate-limit changes; co-location SLA renegotiation; KYC/AML continuity; high value at risk. | Y | Largest single-venue volume contributor; BTC/ETH delta hedges run through Binance; outage = unhedged exposure. | 620 | 110 | 510 | Sep 2025 | In Planning | Engage Binance institutional desk early; parallel-run 4 weeks.
4 | Nasdaq | 4 | Major US equities and options exchange, heavy concentration in technology and growth names. | Primary venue for tech-sector equity exposure; deep options liquidity for hedging single-name positions. | 265000 | 510 | 1650 | Listed Equities, Options | Migrate market data feed and order entry gateway to in-house infrastructure. | Market data licensing renegotiation; options margin treatment differences; gateway certification timeline. | Y | Concentrated tech exposure runs through Nasdaq; options hedges are time-sensitive and execution-critical. | 470 | 95 | 375 | Nov 2025 | Scoping | Begin Nasdaq market data licensing renewal process early.
5 | EBS (CME FX) | 5 | Institutional interbank FX trading platform for spot and forward FX. | Primary venue for G10 FX spot execution; required for currency overlay hedging on international positions. | 640000 | 410 | 2200 | FX Spot, FX Forwards | Migrate FX execution algos and credit line management to proprietary system. | Credit line / prime brokerage continuity; FX settlement (CLS) timing; algo execution recalibration. | Y | Currency overlay hedges run continuously; disruption creates immediate unhedged FX exposure on international book. | 390 | 85 | 305 | Sep 2025 | Scoping | Confirm CLS settlement membership transfers cleanly.
6 | Polymarket | 6 | Leading decentralised prediction & perpetuals market; highest perpetual trade flow in the portfolio. | Primary source of high-frequency perpetual contract flow; superior liquidity depth on crypto perps; critical for short-dated positioning. | 4200 | 310 | 1850 | Crypto Perpetuals, Prediction Contracts | Full API migration of perps order routing and position management to in-house execution layer. | High latency risk during cutover; smart-contract settlement differences; regulatory classification of prediction contracts. | Y | Highest perpetual trade volume; any disruption directly impacts daily book P&L and margin utilisation. | 480 | 95 | 385 | Aug 2025 | In Planning | Prioritise sandbox testing with full order-book replay before go-live.
7 | Deribit | 7 | Leading crypto options and futures exchange, dominant in BTC/ETH options liquidity. | Primary venue for crypto options strategies; deepest order book for BTC/ETH vol trading. | 18500 | 310 | 1400 | Crypto Options, Crypto Futures | Migrate options pricing feed and execution algos to in-house vol desk infrastructure. | Options liquidity concentration risk; API throttling at high volume; offshore regulatory status. | Y | Crypto options book is a major P&L driver; Deribit has no comparable liquidity alternative. | 310 | 65 | 245 | Sep 2025 | In Planning | Coordinate with vol desk on parallel execution testing.
8 | Eurex | 8 | Leading European derivatives exchange for equity index and interest rate futures. | Core venue for European rates and index futures hedging, complementing CME for global macro book. | 145000 | 310 | 890 | Interest Rate Futures, Equity Index Futures | Migrate clearing and execution connectivity to in-house European desk infrastructure. | EU clearing member transfer; margin methodology alignment with CME positions; Brexit-related access rules. | Y | European leg of the global macro hedge; gaps here leave regional rate exposure unhedged. | 280 | 60 | 220 | Dec 2025 | Planned | Align migration timing with CME to keep margin netting benefits.
9 | CBOE | 9 | Largest US options exchange; primary venue for index options and volatility products. | Core venue for VIX and SPX options used in portfolio hedging and volatility strategies. | 98000 | 290 | 980 | Index Options, VIX Futures | Migrate options execution algos and Greeks risk feed to in-house systems. | Complex options margining (SPAN); volatility product settlement timing; market maker relationship continuity. | Y | Volatility hedges are central to the book's tail-risk protection; any gap exposes the fund to unhedged drawdowns. | 350 | 75 | 275 | Nov 2025 | Scoping | Validate Greeks calculation parity between vendor and in-house before cutover.
10 | Coinbase | 10 | Largest US-regulated crypto exchange; key venue for compliant institutional crypto access. | Provides regulatory-clean custody and execution for US-domiciled crypto exposure; required for certain mandates. | 24000 | 260 | 1100 | Spot Crypto, Custody, Staking | Migrate custody reporting and execution API to in-house, retaining Coinbase Prime relationship. | Custody segregation requirements; SEC regulatory status uncertainty; API rate limits on institutional tier. | Y | Only US-regulated venue for several crypto mandates; compliance exposure if connectivity lapses. | 340 | 70 | 270 | Nov 2025 | Scoping | Confirm Coinbase Prime custody arrangement is unaffected by API migration.
11 | Tradeweb | 11 | Institutional fixed income and FX trading platform, key venue for bond and rates execution. | Primary venue for government bond and credit execution supporting the fixed income book. | 210000 | 260 | 780 | Government Bonds, Credit, FX Swaps | Migrate fixed income RFQ workflow and execution to in-house fixed income desk system. | Dealer panel continuity; RFQ protocol complexity; credit market liquidity fragmentation. | Y | Core fixed income execution venue; bond book liquidity sourcing is concentrated here. | 330 | 72 | 258 | Nov 2025 | Scoping | Coordinate closely with fixed income desk on RFQ workflow parity.
12 | Bullish | 12 | Institutional-grade regulated crypto exchange with deep order books and embedded market-making. | Preferred institutional venue for large-size trades and regulatory reporting; MiCA-aligned. | 6800 | 180 | 720 | Spot Crypto, Block Trades, Staking | Transition block-trade workflow and custody reporting to native platform. | FIX protocol customisation effort; fewer counterparties vs Binance; slippage risk during migration. | Y | Regulated venue required for compliance reporting; large block orders cannot easily reroute to alternatives. | 290 | 60 | 230 | Oct 2025 | Scoping | Obtain FIX spec from Bullish institutional team.
13 | LSEG (London Stock Exchange) | 13 | Primary UK/European listed equities exchange. | Required for European equity exposure and GBP-denominated index strategies. | 58000 | 160 | 520 | Listed Equities, ETFs | Migrate European DMA connectivity and MiFID II reporting to in-house gateway. | MiFID II transaction reporting continuity; European market data licensing; timezone overlap for support. | Y | MiFID II reporting obligations are compliance-critical; cannot have a reporting gap on European trades. | 240 | 55 | 185 | Nov 2025 | Scoping | Engage compliance early on MiFID II RTS 27/28 reporting continuity.
14 | MarketAxess | 14 | Leading electronic credit trading platform, dominant in corporate bond execution. | Primary venue for corporate credit execution, particularly investment-grade and high-yield bonds. | 68000 | 140 | 460 | Corporate Bonds, Credit Derivatives | Migrate credit execution algos and bond pricing feed to in-house fixed income infrastructure. | Credit liquidity concentration; dealer relationship continuity; bond pricing feed licensing. | Y | Primary credit execution venue; corporate bond book has limited alternative liquidity sources. | 215 | 48 | 167 | Dec 2025 | Scoping | Validate bond pricing feed parity before migrating execution flow.
15 | Hong Kong Exchanges (HKEX) | 15 | Primary Hong Kong equities exchange, key gateway to mainland China exposure via Stock Connect. | Required for Asia-ex-Japan equity exposure and China A-share access via Connect programme. | 61000 | 110 | 360 | Listed Equities, Stock Connect, Derivatives | Migrate Stock Connect quota management and execution routing to in-house systems. | Stock Connect quota/regulatory complexity; China access restrictions; settlement cycle differences (T+0/T+1). | Y | Stock Connect access is regulatory-sensitive and quota-managed; mishandling risks loss of China market access. | 225 | 50 | 175 | Feb 2026 | Planned | Legal review of Stock Connect quota transfer requirements.
16 | BSE (Bombay Stock Exchange) | 16 | Major Indian equities exchange alongside NSE, used for India equity exposure. | Required for India equity allocation within emerging markets strategy. | 28000 | 50 | 180 | Listed Equities | Migrate India market access and FPI (Foreign Portfolio Investor) reporting to in-house systems. | FPI registration complexity; local custodian relationship; capital controls and repatriation rules. | Y | FPI registration and reporting obligations are compliance-critical for continued India market access. | 170 | 40 | 130 | Mar 2026 | Planned | Engage local custodian and compliance early on FPI continuity.
17 | LMX (LedgerX) | 17 | CFTC-regulated crypto derivatives exchange focused on physically-settled Bitcoin options and futures. | Sole source of physically-settled BTC options; required for regulatory capital treatment of certain positions. | 950 | 45 | 210 | BTC Options (Physical), BTC Futures | Migrate CFTC-reportable trade booking and margin calls to in-house middle-office. | CFTC reporting must not lapse; complex margining; limited tail-strike liquidity; long clearing approval lead time. | Y | CFTC-regulated; physically-settled options require specific clearing setup; compliance breach risk if mishandled. | 175 | 40 | 135 | Dec 2025 | Scoping | Legal review of CFTC reporting obligations before any cutover.
18 | ICE Futures | 18 | Global derivatives exchange for energy, agricultural, and financial futures including Brent crude. | Used for commodity exposure hedging, particularly energy-linked macro positions. | 156000 | 220 | 710 | Energy Futures, Agricultural Futures | Migrate clearing connectivity and futures order routing to in-house OMS. | Clearing member transfer; physical delivery logistics for certain contracts; margin call timing. | N | Commodity hedges are tactical rather than core; some flexibility on migration timing exists. | 260 | 55 | 205 | Jan 2026 | Planned | Sequence after CME given overlapping clearing infrastructure work.
19 | OKX | 19 | Major global crypto exchange with strong derivatives and perpetuals offering. | Secondary perpetuals venue providing redundancy and additional liquidity outside Binance/Polymarket. | 42000 | 180 | 820 | Crypto Spot, Perpetuals, Options | Migrate perpetuals execution and funding rate monitoring to in-house system. | Offshore regulatory status; geo-restriction compliance; lower liquidity depth vs Binance in stress events. | N | Secondary/redundancy venue; primary perp flow runs through Polymarket and Binance. | 220 | 50 | 170 | Jan 2026 | Planned | Lower priority; functions as liquidity backstop only.
20 | Refinitiv FXall | 20 | Multi-bank FX trading platform aggregating liquidity from major dealing banks. | Used for larger FX block trades and RFQ-based execution where EBS liquidity is insufficient. | 180000 | 140 | 640 | FX Spot, FX Forwards, FX Swaps | Migrate RFQ workflow and dealer panel management in-house. | Dealer relationship continuity; RFQ protocol differences; liquidity provider onboarding lag. | N | Secondary FX venue; EBS can absorb most flow short-term if migration is delayed. | 165 | 40 | 125 | Dec 2025 | Planned | Lower urgency; can follow EBS migration by one quarter.
21 | Japan Exchange Group (JPX) | 21 | Primary Japanese equities and derivatives exchange including Nikkei 225 futures. | Used for Japan equity exposure and Nikkei index hedging within the global equity book. | 72000 | 130 | 410 | Listed Equities, Nikkei 225 Futures | Migrate Tokyo-hours execution connectivity and local clearing relationship in-house. | Timezone coverage gap for support; local clearing member requirements; yen settlement timing. | N | Japan exposure is a smaller book segment; some delay tolerance exists if local desk coverage is maintained. | 195 | 45 | 150 | Feb 2026 | Planned | Confirm Tokyo desk coverage hours before scheduling cutover.
22 | Kraken | 22 | US-based regulated crypto exchange with strong spot and staking services. | Used for compliant spot crypto exposure and staking yield generation on idle crypto balances. | 9200 | 95 | 480 | Spot Crypto, Staking, Futures | Migrate spot execution and staking reward reconciliation to in-house treasury system. | Staking reward tax treatment; custody insurance continuity; US regulatory licensing scope changes. | N | Secondary spot venue; staking yield is incremental, not core to strategy P&L. | 150 | 35 | 115 | Jan 2026 | Planned | Bundle with Coinbase migration given overlapping US compliance review.
23 | Singapore Exchange (SGX) | 23 | Key Asian derivatives exchange, dominant in offshore China A50 and Asian FX futures. | Used for Asia-ex-Japan macro hedging and offshore China exposure via A50 futures. | 38000 | 85 | 290 | Equity Index Futures, FX Futures, Commodities | Migrate execution connectivity for offshore Asia futures book to in-house OMS. | Lower liquidity in stress events vs CME/Eurex; clearing member onboarding timeline. | N | Tactical hedging venue; positions can be temporarily managed via OTC alternatives if migration slips. | 160 | 38 | 122 | Feb 2026 | Planned | Lowest priority within futures group; sequence last.
24 | Bybit | 24 | Major crypto derivatives exchange with strong perpetuals and options volume. | Tertiary perpetuals venue providing additional redundancy and arbitrage opportunities. | 31000 | 75 | 340 | Perpetuals, Options | Migrate perpetuals execution and funding arbitrage monitoring in-house. | Offshore regulatory status; geo-restriction risk; lower institutional-grade support vs top-tier venues. | N | Used for arbitrage and redundancy; not core to primary execution strategy. | 140 | 32 | 108 | Mar 2026 | Planned | Evaluate ongoing necessity post-migration of primary venues.
25 | Cboe FX | 25 | Institutional FX trading venue offering spot, forwards, and NDFs. | Secondary FX venue used for NDF execution on emerging market currency exposure. | 95000 | 70 | 310 | FX Spot, NDFs | Migrate NDF execution workflow and EM currency settlement to in-house system. | NDF settlement complexity; counterparty credit lines; EM currency liquidity constraints. | N | EM currency hedging is a smaller book segment; some delay tolerance exists. | 130 | 32 | 98 | Feb 2026 | Planned | Coordinate NDF migration with FX overlay desk.
26 | 360T | 26 | Multi-dealer FX platform popular for corporate and institutional FX execution in Europe. | Used for EUR-cross FX execution and European FX liquidity sourcing. | 110000 | 60 | 260 | FX Spot, FX Forwards | Migrate dealer panel and execution workflow to proprietary FX desk infrastructure. | Dealer relationship continuity; European regulatory (MiFID II) execution reporting requirements. | N | Secondary European FX venue; EBS/FXall can absorb flow short-term. | 120 | 30 | 90 | Mar 2026 | Planned | Sequence after primary FX venues (EBS, FXall).
27 | Bitfinex | 27 | Established crypto exchange with deep margin trading and lending markets. | Used for crypto margin financing and occasional liquidity sourcing during volatility events. | 6500 | 55 | 240 | Spot Crypto, Margin Trading, Lending | Migrate margin financing connectivity and lending desk integration in-house. | Historical regulatory scrutiny; counterparty concentration risk; lower institutional liquidity vs top-tier venues. | N | Used opportunistically rather than as a core execution venue; lower migration urgency. | 110 | 28 | 82 | Mar 2026 | Planned | Monitor counterparty risk; deprioritise unless usage increases.
28 | Bitstamp | 28 | One of the oldest regulated crypto exchanges, strong EU regulatory standing. | Provides EU-regulated crypto access complementing Coinbase's US coverage. | 4100 | 40 | 190 | Spot Crypto | Migrate EU-regulated execution and custody reporting to in-house system. | EU MiCA licensing transition; smaller liquidity pool; redundant coverage with Coinbase/Kraken. | N | Redundant EU coverage; can be migrated opportunistically without urgency. | 95 | 22 | 73 | Mar 2026 | Planned | Low-priority; consider consolidating into Coinbase/Kraken coverage instead.
29 | B3 (Brazil Exchange) | 29 | Primary Brazilian exchange for equities and futures, key Latin America gateway. | Used for Brazil/LatAm equity and rates futures exposure within EM allocation. | 19000 | 35 | 140 | Listed Equities, Interest Rate Futures | Migrate LatAm execution connectivity and local clearing relationship in-house. | Local clearing member requirements; BRL currency controls; lower English-language vendor support. | N | Smaller EM allocation segment; some delay tolerance exists. | 150 | 36 | 114 | Apr 2026 | Planned | Lowest priority in equities group; sequence last.
30 | Johannesburg Stock Exchange (JSE) | 30 | Primary South African exchange, gateway to broader African market exposure. | Used for limited Africa-exposure equity allocation within EM strategy. | 8500 | 18 | 75 | Listed Equities | Migrate execution connectivity for African equity allocation to in-house systems. | Currency controls (ZAR); local settlement infrastructure; small allocation size reduces urgency. | N | Smallest allocation in the portfolio; minimal migration urgency. | 85 | 22 | 63 | Apr 2026 | Planned | Candidate for deferral beyond initial migration wave if resourcing is constrained.
TOTALS / AGGREGATES |  |  |  |  | 3215750 | 6598 | 25605 | [5 empty] | 8115 | 1730 | 6385
LEGEND
Priority 1-10 | Wave 1 — Aug–Nov 2025
Priority 11-20 | Wave 2 — Nov 2025–Feb 2026
Priority 21-30 | Wave 3 — Feb–Apr 2026
Critical = Y | Board-notifiable risk
In Planning | Vendor review stage
Scoping | Technical design stage
Planned | Queued, not yet started

## Milestone Timeline
MIGRATION MILESTONE TIMELINE ¦ Vendor Decommission Programme
Phase | Milestone | Owner | Exchange(s) | Start Date | End Date | Status | Notes
0 – Discovery | Vendor contract review & cost audit | CFO / Legal | All 30 | 01 Jun 2025 | 15 Jun 2025 | Complete | Confirmed total annual vendor spend across all venues
0 – Discovery | Internal system capability assessment | CTO / Engineering | All 30 | 01 Jun 2025 | 20 Jun 2025 | Complete | In-house OMS confirmed extensible across asset classes
1 – Design | Architecture sign-off for in-house execution layer | CTO | All 30 | 21 Jun 2025 | 05 Jul 2025 | In Progress | Draft reviewed; board approval pending
1 – Design | Wave 1 connectivity specs finalised (Priority 1-10) | Engineering | Wave 1 | 05 Jul 2025 | 25 Jul 2025 | Planned | Polymarket, Binance, CME, NYSE, EBS, Tradeweb, Deribit, etc.
2 – Build | Wave 1 in-house execution build & unit testing | Engineering | Wave 1 | 21 Jul 2025 | 20 Aug 2025 | Planned | Parallel build with vendor still live
2 – Build | Wave 1 sandbox UAT & order-book replay | Engineering / Risk | Wave 1 | 10 Aug 2025 | 30 Aug 2025 | Planned | Highest-volume venues tested first
3 – Migration | Wave 1 LIVE cutover (top 10 by priority) | CTO / Trading Desk | Wave 1 | 18 Aug 2025 | 30 Nov 2025 | Planned | Rolling cutovers; weekend windows; rollback plans ready
1 – Design | Wave 2 connectivity specs finalised (Priority 11-20) | Engineering | Wave 2 | 01 Oct 2025 | 20 Oct 2025 | Planned | LSEG, Eurex, JPX, HKEX, SGX, Bitfinex, Bitstamp, etc.
2 – Build | Wave 2 build & UAT | Engineering / Risk | Wave 2 | 20 Oct 2025 | 20 Dec 2025 | Planned | Includes Asia-hours support coordination
3 – Migration | Wave 2 LIVE cutover | CTO / Trading Desk | Wave 2 | 01 Dec 2025 | 28 Feb 2026 | Planned | Sequenced regionally to manage desk coverage
1 – Design | Wave 3 connectivity specs finalised (Priority 21-30) | Engineering | Wave 3 | 01 Jan 2026 | 20 Jan 2026 | Planned | Cboe FX, 360T, Bybit, BSE, B3, JSE, MarketAxess
2 – Build | Wave 3 build & UAT | Engineering / Risk | Wave 3 | 20 Jan 2026 | 20 Mar 2026 | Planned | Lower-volume/redundant venues; flexible scheduling
3 – Migration | Wave 3 LIVE cutover | CTO / Trading Desk | Wave 3 | 01 Mar 2026 | 30 Apr 2026 | Planned | Final wave; smallest allocations migrated last
3 – Migration | LMX legal & CFTC reporting review | Legal / Compliance | LMX | 01 Oct 2025 | 30 Oct 2025 | Planned | Legal sign-off required before any system changes
3 – Migration | FPI / Stock Connect compliance reviews (India, HK) | Legal / Compliance | BSE, HKEX | 01 Dec 2025 | 31 Jan 2026 | Planned | Required before any EM equity venue cutover
4 – Closure | Vendor system decommission notice issued | CFO / Legal | All 30 | 01 Apr 2026 | 01 Apr 2026 | Planned | 30-day notice period per contract
4 – Closure | Full vendor decommission & contract termination | CFO | All 30 | 15 Apr 2026 | 30 Apr 2026 | Planned | Target: zero vendor dependency by 01 May 2026
5 – Review | Post-migration cost & performance review | CFO / CTO | All 30 | 01 May 2026 | 31 May 2026 | Planned | Report cost savings vs projection to board

## Cost Savings Summary
COST SAVINGS ANALYSIS ¦ Vendor → In-House Migration ¦ 30 Exchanges
Exchange | Annual Vendor Cost ($K) | Annual In-House Cost ($K) | Annual Saving ($K) | 3-Year Saving ($K) | 5-Year Saving ($K)
CME Group | 710 | 140 | 570 | 1710 | 2850
NYSE | 540 | 105 | 435 | 1305 | 2175
Binance | 620 | 110 | 510 | 1530 | 2550
Nasdaq | 470 | 95 | 375 | 1125 | 1875
EBS (CME FX) | 390 | 85 | 305 | 915 | 1525
Polymarket | 480 | 95 | 385 | 1155 | 1925
Deribit | 310 | 65 | 245 | 735 | 1225
Eurex | 280 | 60 | 220 | 660 | 1100
CBOE | 350 | 75 | 275 | 825 | 1375
Coinbase | 340 | 70 | 270 | 810 | 1350
Tradeweb | 330 | 72 | 258 | 774 | 1290
Bullish | 290 | 60 | 230 | 690 | 1150
LSEG (London Stock Exchange) | 240 | 55 | 185 | 555 | 925
MarketAxess | 215 | 48 | 167 | 501 | 835
Hong Kong Exchanges (HKEX) | 225 | 50 | 175 | 525 | 875
BSE (Bombay Stock Exchange) | 170 | 40 | 130 | 390 | 650
LMX (LedgerX) | 175 | 40 | 135 | 405 | 675
ICE Futures | 260 | 55 | 205 | 615 | 1025
OKX | 220 | 50 | 170 | 510 | 850
Refinitiv FXall | 165 | 40 | 125 | 375 | 625
Japan Exchange Group (JPX) | 195 | 45 | 150 | 450 | 750
Kraken | 150 | 35 | 115 | 345 | 575
Singapore Exchange (SGX) | 160 | 38 | 122 | 366 | 610
Bybit | 140 | 32 | 108 | 324 | 540
Cboe FX | 130 | 32 | 98 | 294 | 490
360T | 120 | 30 | 90 | 270 | 450
Bitfinex | 110 | 28 | 82 | 246 | 410
Bitstamp | 95 | 22 | 73 | 219 | 365
B3 (Brazil Exchange) | 150 | 36 | 114 | 342 | 570
Johannesburg Stock Exchange (JSE) | 85 | 22 | 63 | 189 | 315
TOTAL | 8115 | 1730 | 6385 | 19155 | 31925
Note: Estimated one-time in-house build cost: $950K (engineering + infra across all 30 venues, phased over 3 waves). Full payback within ~10 months of Wave 1 completion.

## Risk Register
PROGRAMME RISK REGISTER ¦ Exchange Migration ¦ CONFIDENTIAL
Risk ID | Risk Category | Risk Description | Affected Exchange(s) | Likelihood (1-5) | Impact (1-5) | Risk Score (L×I) | Risk Level | Mitigation / Control | Owner | Status | Target Close Date
R-01 | Operational | Trading disruption / missed fills during live cutover window on high-volume venues. | Polymarket, Binance, CME, NYSE | 4 | 5 | 20 | Critical | Weekend/low-volume cutover windows; rollback plan tested in advance; vendor kept on hot-standby for 30 days post-cutover. | CTO / Trading Desk | Open | 31 Aug 2025
R-02 | Compliance | CFTC reporting obligations lapse during LMX system transition, resulting in regulatory breach. | LMX | 2 | 5 | 10 | High | Legal review and sign-off required before any system change; dry-run reporting parity test pre-cutover. | General Counsel | Open | 30 Oct 2025
R-03 | Compliance | MiFID II / MiCA transaction reporting gap during European venue migration. | LSEG, Eurex, Bullish | 2 | 5 | 10 | High | Compliance engaged from design phase; RTS 27/28 reporting parity validated in UAT before go-live. | Compliance | Open | 30 Nov 2025
R-04 | Operational | FX settlement (CLS) membership disruption during EBS/FXall migration causing failed settlements. | EBS, FXall, Tradeweb | 3 | 5 | 15 | Critical | Confirm CLS membership transfer with operations team; parallel-run settlement instructions for 2 weeks. | Treasury Ops | Open | 30 Sep 2025
R-05 | Financial | One-time build cost overrun beyond approved $950K budget across 30-venue programme. | All | 3 | 3 | 9 | High | Phased wave-based budget tracking; monthly cost review against plan; contingency buffer of 15% built in. | CFO | Open | Ongoing
R-06 | Operational | Co-location and direct market access (DMA) SLA renegotiation delays for CME/NYSE/Nasdaq. | CME, NYSE, Nasdaq | 3 | 4 | 12 | High | Early engagement with exchange co-location teams; legal review of new SLA terms in parallel with build phase. | CTO / Legal | Open | 31 Oct 2025
R-07 | Operational | Margin methodology mismatch (SPAN vs in-house) causing incorrect margin calls post-migration. | CME, Eurex, CBOE | 3 | 4 | 12 | High | Shadow-run margin calculations for 4 weeks pre-cutover; reconcile daily against vendor figures before go-live. | Risk / Engineering | Open | 30 Nov 2025
R-08 | Regulatory | Stock Connect quota / FPI registration complications during HKEX and BSE migration. | HKEX, BSE | 3 | 5 | 15 | Critical | Dedicated legal workstream for EM equity venues; confirm quota transfer mechanics with local custodians. | Legal / Compliance | Open | 31 Jan 2026
R-09 | Technology | API rate-limit or throughput changes imposed by exchanges (esp. Binance) during institutional re-onboarding. | Binance, Deribit, OKX, Bybit | 3 | 4 | 12 | High | Direct engagement with exchange institutional desks; negotiate dedicated rate limits ahead of cutover. | Engineering | Open | 30 Sep 2025
R-10 | Operational | Smart-contract settlement timing differences on Polymarket causing reconciliation breaks. | Polymarket | 3 | 3 | 9 | High | Full order-book and settlement replay in sandbox; reconciliation tooling built before go-live. | Engineering / Risk | Open | 15 Aug 2025
R-11 | People / Resourcing | Engineering resource overrun or attrition during 3-wave, ~10-month build programme. | All | 3 | 3 | 9 | High | Phased approach allows re-sequencing; cross-training across exchange workstreams; contractor backup identified. | CTO | Open | Ongoing
R-12 | Vendor / Contractual | Vendor imposes early-termination penalties or disputes notice period during decommission. | All | 2 | 3 | 6 | Medium | Legal review of vendor contract terms completed in Discovery phase; termination notice timed per contract clause. | Legal | Closed | 15 Jun 2025
R-13 | Operational | Custody segregation or insurance coverage gap during Coinbase/Kraken/Bitstamp crypto custody migration. | Coinbase, Kraken, Bitstamp | 2 | 4 | 8 | Medium | Confirm custody arrangements remain with existing prime relationship; insurance coverage continuity letter obtained. | Operations / Legal | Open | 30 Nov 2025
R-14 | Operational | Timezone / desk coverage gaps for APAC and EM venues during cutover (JPX, HKEX, SGX, BSE, B3, JSE). | JPX, HKEX, SGX, BSE, B3, JSE | 3 | 3 | 9 | High | Confirm regional desk coverage hours before scheduling; consider follow-the-sun support model during cutover week. | Trading Desk / Ops | Open | 31 Jan 2026
R-15 | Technology | Market data feed licensing renegotiation delays (Nasdaq, LSEG, JPX) blocking in-house gateway certification. | Nasdaq, LSEG, JPX | 3 | 3 | 9 | High | Initiate market data licensing renewal process at start of Design phase, well ahead of cutover date. | Engineering / Vendor Mgmt | Open | 31 Oct 2025
R-16 | Financial | Realised cost savings fall materially short of $1,260K+ projected annual figure post full migration. | All | 2 | 3 | 6 | Medium | Monthly cost tracking dashboard from Wave 1 go-live; quarterly variance review presented to Investment Committee. | CFO | Open | 31 May 2026
R-17 | Operational | Credit line / prime brokerage relationship disruption during FX and fixed income venue migration. | EBS, FXall, Tradeweb, MarketAxess | 2 | 4 | 8 | Medium | Confirm credit lines transfer without re-underwriting; maintain dual-running credit facilities during transition. | Treasury / Credit | Open | 31 Dec 2025
R-18 | Reputational | Client or counterparty perception of operational risk during a highly visible infrastructure transition. | All | 2 | 3 | 6 | Medium | Proactive, controlled internal and external communication plan; no client-facing disruption permitted during cutover. | CCO / IR | Open | Ongoing
RISK SCORE KEY
Critical (15-25) | Immediate Board/IC visibility required
High (9-14) | Active mitigation, weekly tracking
Medium (4-8) | Monitor, standard programme cadence
Low (1-3) | Accepted risk, periodic review